## Sheet1
TIME SCHEDULE [NEW SITE Out Door, PO DURATION = 30 days
No |  | SoW
No |  | SoW
1 |  | Setting out
2 |  | Man Power
3 |  | Mos Besi Pondasi KS, Pagar Pabrikasi, ME
4 |  | Soil Excavation
5 |  | Rebar
6 |  | MOS Tower Incl. Anchor & Aksesoris
7 |  | Setting Angkur
8 |  | Pouring
9 |  | Curing time
10 |  | Tower Erection & Painting Tower
11 |  | Eqp Foundation
12 |  | M/E
13 |  | Grounding sytem
14 |  | Fence Yard, Access Road
15 |  | Collect Dokumen BAST for ATP
16 |  | Installation Power Solarsel
17 |  | ATP
18 |  | Repair Pending item (if Any) & Prepair Collect Dokumen BAST ( If Any
|  | TIMELINE PROJECT SLING 45 SITE | 43
No |  | DESCRIPTION | TAHALUPU |  |  | TOMI TOMI |  |  | LUMOY |  |  | SIWAR |  |  | NEGERI KILMURY |  |  | SESAR |  |  | LUANG |  |  | TOUNWAWAN |  |  | KELAWIS |  |  | BATU ROTOK |  |  | BATU ATAS |  |  | RONDUMA |  |  | WAWONII TIMUR |  |  | Alila Selatan |  |  | Lawahing |  |  | MUNASELI |  |  | PURA SELATAN |  |  | BALABALAKANG |  |  | SIMBUANG |  |  | NOSU |  |  | ARALLE |  |  | Rauki |  |  | PT PAMA SITE BHARINDO |  |  | DAGASULI |  |  | LEO - LEO |  |  | SOPI |  |  | GELA |  |  | TRIBUR BARUGA |  |  | PROBUR |  |  | PADANG ALANG |  |  | LEDE |  |  | SAMUYA |  |  | DOFA |  |  | PAS IPA |  |  | LIFOFA |  |  | SELAMALOFO |  |  | KOKOTU |  |  | KOTUNANG |  |  | LOLAGURUA LOID |  |  | KAPUTUSANG |  |  | MATUTING |  |  | LEMO LEMO |  |  | WOOI |  |  | HEBING |  |  | HEBING
|  | SoW | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH | DAYS | START | FINISH
1 | PREPARE PROJECT |  | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05 | 8 | 2021-06-30 | 2021-07-05
| 1.1 | PERMIT | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02 | 4 | 2021-06-30 | 2021-07-02
| 1.2 | Mobilisasi Team | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04 | 3 | 2021-07-03 | 2021-07-04
| 1.3 | Foto Before | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05 | 1 | 2021-07-05 | 2021-07-05
2 | PENGADAAN MATERIAL |  | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07 | 7 | 2021-07-02 | 2021-07-07
| 2.1 | SLING & Acsesoris | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06 | 5 | 2021-07-02 | 2021-07-06
| 2.2 | Meterial Alam / Civil | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07 | 2 | 2021-07-07 | 2021-07-07
3 | DELIVERY MATERIAL |  | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30 | 25 | 2021-07-07 | 2021-07-30
| 3.1 | Sortir Material | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07 | 1 | 2021-07-07 | 2021-07-07
| 3.2 | Pick Up | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08 | 2 | 2021-07-08 | 2021-07-08
| 3.3 | MOD | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25 | 17 | 2021-07-09 | 2021-07-25
| 3.4 | MOS | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30 | 5 | 2021-07-26 | 2021-07-30
4 | MINI CME ( PERGANTIAN PONDASI SLING ) |  | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03 | 5 | 2021-07-30 | 2021-08-03
| 4.1 | Galian dan Begesting | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31 | 1 | 2021-07-30 | 2021-07-31
| 4.2 | Pengecoran ( Puring ) | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01 | 1 | 2021-08-01 | 2021-08-01
| 4.3 | Curring Time | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03 | 3 | 2021-08-02 | 2021-08-03
5 | DISMENTLE SLING |  | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05
| 5.1 | Pelepasan Sling Lama | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05 | 2 | 2021-08-03 | 2021-08-05
6 | IMPLEMENTASI SLING BARU |  | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08 | 4 | 2021-08-05 | 2021-08-08
| 6.2 | Pemasangan Sling Baru | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10 | 2 | 2021-08-09 | 2021-08-10
| 6.3 | Tension | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11 | 1 | 2021-08-11 | 2021-08-11
| 6.4 | Verikality | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12 | 1 | 2021-08-12 | 2021-08-12
7 | ATP |  | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14
| 7.1 | ATP | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14 | 2 | 2021-08-13 | 2021-08-14
Formulas:
START = [FINISH, row above]+1